## Slide 1: Maia for PowerPoint
DSTA · MAIA PROJECT EXTENSION
Bringing Maia’s on-premise AI into PowerPoint, on the Qwen model we already run
Project proposal · 23 October 2026
Notes: This proposal extends Maia, our Outlook assistant, into PowerPoint. The key message: we reuse the backend, guardrails and Qwen model we already run, so Phase 1 needs no new model and no new infrastructure.

## Slide 2: Extend Maia into PowerPoint in two phases, on the Qwen model we already run
EXECUTIVE SUMMARY
WHY
Decks hold the same restricted content as email. Public tools cannot touch it, and no on-premise slide assistant exists today.
HOW
Reuse Maia’s backend, guardrails, PII masking, Redis and telemetry. Only image generation needs a new model.
ASK
Approve Phase 0 and Phase 1 (about 10–13 weeks, 1–2 developers) and choose the PowerPoint host technology.
Maia for PowerPoint · Project proposal · 2
Notes: Three points. Why: decks carry restricted content and public assistants can’t be used on them. How: everything except image generation reuses what Maia already runs. Ask: approve Phase 0 and 1, and decide the host technology.

## Slide 3: Decks carry the same restricted content as email, with no AI help
THE PROBLEM
Read
Officers read long briefings and proposals without help.
Present
Speaker notes are written by hand, slide by slide.
Build
New decks are assembled manually from emails and documents.
Copilot in PowerPoint does all three, but it cannot be used on restricted material.
Maia for PowerPoint · Project proposal · 3
Notes: Maia already serves 400–500 concurrent Outlook users. Much of the same content ends up in decks, where officers get no help today. Commercial assistants solve this but can’t be used on restricted content.

## Slide 4: Read the deck first, then write it
SCOPE
Phase | Feature | What the user gets
0 | Foundation | Plugin, deck-to-JSON, /api/ppt endpoints, async jobs
1.1 | Deck summarisation | Summary, decisions and actions, citing slides
1.3 | Speaker notes | Notes per slide by length, tone and audience
1.2 | Prompt to presentation | Editable outline, then slides on the DSTA template
2.1 | Text to visual | Native, editable charts and diagrams
2.3 | Condense and rewrite | Fix overflow, split slides, rewrite for an audience
2.2 | Image generation | Illustrations from an on-premise image model
Out of scope: sending or publishing decks automatically, web search, external model APIs in production.
Maia for PowerPoint · Project proposal · 4
Notes: Phase 1 is text only; shaded rows are Phase 2. We build read-first: summarisation, then notes, then generation, because each reuses the parts of the one before. Image generation comes last because it needs a new model and sign-off.

## Slide 5: Two open-source projects can run on our own models
HOW OTHERS DO IT
Tool | Approach | Lesson for Maia
Copilot in PowerPoint | In-app: drafts, rewrites, writes notes | Our taskpane and chat design matches
Gamma | Topic, outline review, deck in about 1 minute | Make the outline editable
Presenton | Open source, self-hosted, editable PPTX | Candidate engine for prompt-to-deck
PPTAgent | Edits reference slides, keeps their layout | Best fit for the DSTA template
Napkin AI | Picks a visual type, draws an editable diagram | Model for 2.1; keep it source-bound
GovTech Pair | Approved to RESTRICTED; no slide feature found | Fills a gap; copy its value metric
Shaded: open source (Apache 2.0 and academic), both support local, OpenAI-compatible models.
Maia for PowerPoint · Project proposal · 5
Notes: Copilot moved rewrite, translate and speaker notes into a chat-based Agent mode in March–April 2026, which is the same pattern as Maia’s taskpane. Presenton is Apache 2.0 with a FastAPI backend; PPTAgent (EMNLP 2025) and its successor DeepPresenter (ACL 2026) have an offline mode. GovTech’s Pair reports 45 minutes saved per dollar; we found no slide generation in it.

## Slide 6: Outline first, user review, then render
THE COMMON PATTERN
Copilot, Gamma, Presenton and PPTAgent all work this way. The outline is the cheapest place to fix a deck, so Maia will make it editable.
Notes: Every tool we looked at follows the same three steps. They differ only in how they render the final slides, which is the decision we make in the Phase 0 spike.

## Slide 7: New PowerPoint parts sit on Maia’s existing pipeline
Blue: existing Maia components, reused · Dashed: new, Phase 2.2 only · 7
ARCHITECTURE
Workstation
PowerPoint plugin (VSTO)
Reads and writes slides and notes
Maia taskpane (WebView2)
Chat, outline editor, previews
Backend (FastAPI)
/api/ppt router and async job queue
Shared Maia pipeline
Prompt guard · PII masking · safety classifier · token fit
Summary, notes 1.1, 1.3
Outline, render 1.2
Visuals, rewrite 2.1, 2.3
Infrastructure
Qwen3.6-35B-A3B
Redis Sentinel
SQL Server
Image model (2.2)
Notes: The plugin sends the open deck as JSON, so the backend never parses .pptx files from the client. Every request passes the same safety pipeline as Outlook. Generation runs as async jobs in Redis because it can exceed the 120-second LLM timeout. The only new infrastructure is the image model, and only in Phase 2.2.

## Slide 8: Six of seven features run on the Qwen model we already use
MODEL STRATEGY
6 of 7
features on Qwen3.6-35B-A3B, already on-premise and reviewed
262,144-token native context, about 2× today’s setting
Reads images, so alt-text needs no new model
No new procurement for Phase 1
Feature | Model
1.1 Summarisation | Qwen3.6-35B-A3B
1.2 Prompt to deck | Qwen3.6-35B-A3B
1.3 Speaker notes | Qwen3.6-35B-A3B
2.1 Text to visual | Qwen3.6-35B-A3B
2.3 Condense, rewrite | Qwen3.6-35B-A3B
2.4 Alt-text | Qwen3.6-35B-A3B
2.2 Image generation | New: Qwen-Image-2512
Maia for PowerPoint · Project proposal · 8
Notes: Only image generation needs a new model. Qwen-Image-2512 is Apache 2.0, about 64 GB VRAM at full precision or 18–24 GB quantised. We avoid Qwen-Image-2.1 and FLUX.2 dev because of non-commercial licences; Ideogram 4.0 is a paid backup if non-Alibaba provenance is required.

## Slide 9: Capacity, not capability, is the constraint
MODEL STRATEGY
The risk
A 12-slide deck with notes is several thousand output tokens; an email answer is a few hundred. Long jobs on the shared Qwen could slow chat for 400–500 Outlook users.
The mitigation
Redis job queue with a concurrency cap
Lower priority than interactive chat
A dedicated replica only if load tests demand it
If quality falls short
Qwen3.6-27B for generation and rewriting only
DeepPresenter 9B if we adopt PPTAgent
Both behind the same endpoint, after evaluation.
Maia for PowerPoint · Project proposal · 9
Notes: The model can do the work; the question is load. We protect chat latency with a queue and priorities, and only buy more GPU if load tests show we need it. Model swaps are a fallback after the golden-set evaluation, not the starting plan.

## Slide 10: Phase 2 starts only after Phase 1 meets its targets
DELIVERY PLAN
Phase 0–1
0 Foundation
2–3 weeks
1.1 Summarise
2 weeks
1.3 Notes
1–2 weeks
1.2 Generate
3–4 weeks
Gate 1: Phase 1 golden-set targets met
Phase 2
2.1 Visuals
About 3 weeks
2.3 Condense
2–3 weeks
Gate 2: licence and security
2.2 Images
4+ weeks
Phase 0–1: about 10–13 weeks for 1–2 developers. A 2-week rendering spike runs inside Phase 0. Estimates are rough.
Maia for PowerPoint · Project proposal · 10
Notes: Two gates. Phase 2 starts only when Phase 1 hits its golden-set targets. Image generation additionally waits for licence and security sign-off. The rendering spike compares Presenton, PPTAgent and python-pptx on the real DSTA template.

## Slide 11: PowerPoint inherits Maia’s controls; nothing leaves the boundary
SECURITY AND GOVERNANCE
Same pipeline
Prompt guard, PII masking and safety classifier on every call; deck text treated as untrusted data.
No silent changes
Preview and confirm before slides or notes change; Maia never sends or publishes a deck.
Fix first
Close the HLD’s critical issues before rollout: committed secrets, default JWT secret, session IDs not tied to a user.
Images and open source
Image prompt and output checks, AI-generated tags; any open-source engine runs offline after code review.
Maia for PowerPoint · Project proposal · 11
Notes: Decks are at least as sensitive as email, so the open critical issues from the Maia High-Level Design must be closed before PowerPoint rollout. Image generation adds its own guardrails: no real people, logos or classified-looking material, plus a classifier on the generated image.

## Slide 12: Judged on 30 real decks before Phase 2 begins
SUCCESS METRICS
Area | Metric | Proposed target
Summarisation | Faithfulness, no fabricated facts | ≥ 95%
Summarisation | Claims citing the correct slide | ≥ 95%
Generation | Outlines that are valid JSON | ≥ 99%
Generation | Slides with overflowing text | < 5%
Speaker notes | Notes accepted without edits | ≥ 60%
Capacity | Chat p95 latency during jobs | No worse than today
Value | Minutes saved per deck (survey) | Baseline in pilot
Golden set scored on PPTEval’s content, design and coherence; targets are starting points to calibrate.
Maia for PowerPoint · Project proposal · 12
Notes: We need about 30 sanitised real decks for the golden set. PPTEval comes from the PPTAgent research and scores content, design and coherence. Adoption and minutes saved feed management reporting, in the same style as GovTech Pair’s value metric.

## Slide 13: Every main risk has a fallback
RISKS
Risk | Mitigation
Generation jobs slow Outlook chat | Queue, concurrency cap, lower priority; replica if needed
Slides break the DSTA template | Map to template layouts or edit reference slides; test early
Model invents facts | Source-bound mode, slide citations, faithfulness tests
Office.js lacks speaker notes | Use VSTO, or confirm support before choosing
Image licence rejected | Apache 2.0 model first; paid Ideogram or icon library
Open HLD security issues | Close the critical issues before rollout
Maia for PowerPoint · Project proposal · 13
Notes: The biggest operational risk is load on the shared Qwen server. The biggest quality risk is the DSTA template, which is why the rendering spike uses the real .potx file. The host technology question matters because speaker notes depend on it.

## Slide 14: Five decisions start Phase 0
DECISIONS REQUESTED
Approve Phase 0 and Phase 1 on Qwen3.6-35B-A3B
Choose the host: VSTO with WebView2 (recommended) or Office.js
Choose rendering after a 2-week spike: Presenton, PPTAgent or python-pptx
Provide the DSTA .potx template and 30 sanitised decks
Start the licence and security review for image generation
Resources: 1–2 developers for about 12–13 weeks, part-time security review, no new infrastructure for Phase 1.
Notes: Close on the ask. The first and second decisions unblock Phase 0 immediately; the template and sample decks are needed for the rendering spike and the golden set. Image generation can be reviewed in parallel without delaying Phase 1.